## Time Line
Days | Mision | Goals | Details
2025-10-12 | Rule-Book | IRC IGVC URC ERC UGVC(EGYPT)
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17 |  |  | Meeting
2025-10-18 | Initial Design | الشكل اللى كل واحد هيشتغل عليه الفتره الجايه
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24 |  |  | Meeting
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31 |  |  | Meeting
2025-11-01 | Design & Optimization | Final Design
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07 |  |  | Meeting
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14 |  |  | Meeting
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21 |  |  | Meeting
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28 |  |  | Meeting
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05 |  |  | Meeting
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12 |  |  | Meeting
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17 |  |  | Preparing Final Purchase
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27 | Manufaturing
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16 | Testing | Run internal ERC-style tasks (sample retrieval, analysis, reporting). Adjust hardware/software.
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
Formulas:
Days = [Days, row above]+1

## Competitions
Milestone | Deliverable / Event | Date | Location | Submission Format | Judging Criteria
Kick-Off (KO) | Rules Publication / Registration Start | 10th February 2026 | Kraków, Poland | Online Form / Document | Rule Adherence
KO: Registration End | Registration Forms + Proposal | 10th March 2026 | Kraków, Poland | PDF | Completeness
Preliminary Design Review (PDR-1) | Preliminary Report + Preliminary RF Form | 6th April 2026 | Kraków, Poland | PDF / Online Form | Technical Feasibility
PDR-2 / QUALIFICATION | Video Material Delivery | 1st June 2026 | Kraków, Poland | MP4 | Rover Functionality
Qualification Announcement | Teams are notified of qualification status. | 29th June 2026 | Kraków, Poland | Email | Qualification Score
Critical Design Review (CDR-1) | Final Report + Final RF Form | 26th July 2026 | Kraków, Poland | PDF / Online Form | Design Robustness
Update Report #3 | Mars Yard Details Released | 8th August 2026 | Kraków, Poland | Web Page | N/A
Exploration Task Readiness Review (E-TRR) | Science Planning Report | 18th August 2026 | Kraków, Poland | PDF | Scientific Method
Droning Sub-Task Report | Report delivery | 26th August 2026 | Kraków, Poland | PDF | Drone Autonomy
Competition Start | Registration and warm-up day | 28th August 2026 | Kraków, Poland | In-person | Punctuality
ERC Finals | ERC Tasks competition period | 29th August–31st August 2026 | Kraków, Poland | In-person | Task Performance
Presentation Task | Presentation File delivery | 30th August 2026 | Kraków, Poland | PPTX | Clarity / Content
Closing ceremony | Awards presentation | 31st August 2026 | Kraków, Poland | In-person | N/A
Milestone | Deliverable / Event | Date | Location | Submission Format | Judging Criteria
Registration | Registration window is open | September 26 to October 26, 2026 | Goa, India | Online Form | Timeliness
Early Bird Offer | Discount deadline for Finals registration fee | October 5, 2026 | Goa, India | Online Payment | N/A
SDDR | System Design and Development Review (SDDR) Package | November 10, 2026 | Goa, India | PDF / Video | Design Innovation
Wildcards | Live presentation deadline for wildcard entries | before November 10, 2026 | Goa, India | Online Presentation | Novelty / Potential
Comms Standards | Notification of communication standards to organizers | December 1, 2026 | Goa, India | Email | Technical Compliance
Finals Confirmation | Teams must confirm their participation in the Finals | December 5, 2026 | Goa, India | Online Form | Commitment
IRC Finals | Competition period | January 28 - February 2, 2026 | Goa, India | In-person | Task Performance
Milestone | Deliverable / Event | Date | Location | Submission Format | Judging Criteria
Registration | Declaration of intent to compete | no later than Friday, March 14, 2026 | Egypt | Online Form | Timeliness
PDR | Preliminary Design Review (PDR) submission | no later than Friday, March 28, 2026 | Egypt | PDF | Technical Feasibility
PDR Notification | Teams notified of acceptance status | by Friday, April 26, 2026 | Egypt | Email | PDR Score
Technical Report | Technical Report submission | no later than Thursday, July 10, 2026 | Egypt | PDF | Engineering Details
Competition | UGVC-9 Events | July 26 to 31, 2026 | Egypt | In-person | Task Performance
Milestone | Deliverable / Event | Date | Location | Submission Format | Judging Criteria
Registration | Team Intent to Compete | no later than Friday, February 7, 2026 | Rochester, Michigan, USA | Online Form | Timeliness
Design Report | Concept Design Report Submission | no later than Friday, March 21, 2026 | Rochester, Michigan, USA | PDF | Innovation / Feasibility
Safety Paper | Autonomous Navigation Safety Document | no later than Friday, April 18, 2026 | Rochester, Michigan, USA | PDF | Safety Protocols
Technical Inspection | Vehicle Pre-Competition Check | no later than Thursday, June 5, 2026 | Rochester, Michigan, USA | On-site Inspection | Compliance / Readiness
Competition Days | Autonomous Challenge Events | June 6-8, 2026 | Rochester, Michigan, USA | In-person | Performance / Reliability
Awards Ceremony | Recognition and Prizes | Sunday, June 8, 2026 | Rochester, Michigan, USA | In-person | N/A
Milestone | Deliverable / Event | Date | Location | Submission Format | Judging Criteria
Registration | Declaration of intent to compete | no later than Wednesday, October 30, 2024 | Hanksville, Utah | Online Form | Timeliness
PDR | Preliminary Design Review Document | no later than Wednesday, December 4, 2024 | Hanksville, Utah | PDF | Technical Feasibility
SAR | System Acceptance Review (written and video components) | no later than Friday, February 28, 2026 | Hanksville, Utah | PDF / MP4 | System Compliance
Communication Info | Communication devices and operator licenses details submitted | no later than Friday, April 25, 2026 | Hanksville, Utah | Online Form | Regulatory Adherence
Final Expense Report | Final Rover Expense Report | no later than May 21, 2026 | Hanksville, Utah | Spreadsheet | Financial Transparency
Field Competition | URC Finals | May 28-31, 2026 | Hanksville, Utah | In-person | Task Performance

## General Rules & Guidence
Category | Rule/Condition
**General Rules** | Every team member must show total commitment to assigned tasks.
No excuses will be accepted for incomplete or delayed work During Manufacturing
A mandatory meeting will be held every Friday at 4:00 PM.
**Evaluation System** | Each week, evaluate members based on their completed tasks.
Each task’s value depends on the total number of tasks assigned during the month, meaning one task can represent up to 100% of a member’s evaluation.
Monthly evaluation score must be 20 or above to remain in the project.
**Elimination Conditions** | Failure to submit tasks two consecutive times leads to elimination.
Having a monthly evaluation score below 20 results in elimination.