## initially
Phase | Duration | Goals
Phase 1: Team Setup & Training | 4–6 weeks | Train beginners on basics (electronics, coding, mechanical CAD, science task rules). Assign sub-teams.
Phase 2: Design & Simulation | 4–6 weeks | CAD models for manipulator, corer, spectrometer mount. ROS2/Gazebo simulation of rover + manipulator.
Phase 3: Prototyping Subsystems | 6–8 weeks | Build manipulator (low-cost servos → later upgrade), test corer prototype, integrate handheld spectrometer.
Phase 4: Integration & Field Testing | 6–10 weeks | Assemble rover with manipulator & sensors. Train operators. Develop data analysis + reporting workflow.
Phase 5: Mock Missions & Polish | 4 weeks | Run internal ERC-style tasks (sample retrieval, analysis, reporting). Adjust hardware/software.